## Sheet1
Category | Code | Category Item | Spec : | Durasi (Days) | Qty | Satuan
Manpower
Manpower | MP00028 | Manager | Project Manager | 145 | 1 | Org
Manpower | MP00025 | Manager | Site Manager | 145 | 1 | Org
Manpower | MP00037 | Staff | Site Engineer | 145 | 2 | Org
Manpower | - | - | Supervisor | 145 | 3 | Org
Manpower | MP00033 | Supervisor | Quality Control | 145 | 2 | Org
Manpower | MP00032 | Supervisor | HSE | 145 | 1 | Org
Manpower | MP00049 | Supervisor | Logistic | 145 | 2 | Org
Manpower | MP00068 | Staff | Surveyor | 145 | 1 | Org
Manpower | MP00041 | Staff | Drafter | 145 | 1 | Org
Manpower | MP00048 | Supervisor | Rigger Lifting | 145 | 1 | Org
Manpower | MP00053 | Staff | Admin & GA | 145 | 2 | Org
Manpower | MP00058 | Worker Driver | Driver | 145 | 1 | Org
Manpower | MP00054 | Worker Security | Security | 145 | 3 | Org
Consumable
Consumable | CN000010 | Abrasive | Diamonds Wheels 4" | 145 | 60 | Pcs
Consumable | CN01972 | Abrasive | Batu gerinda 4" x 6 " mmt | 145 | 450 | Pcs
Consumable | CN00009 | Abrasive | Sand Paper Disc 4" (Amplas Gerinda) | 145 | 450 | Pcs
Consumable | CN00001 | Alat Laminasi | Roll Kapas 4" | 145 | 230 | Pcs
Consumable | CN00002 | Alat Laminasi | Roll Kapas 8" | 145 | 115 | Pcs
Consumable | CN00003 | Alat Laminasi | Roll Besi | 145 | 30 | Pcs
Consumable | CN00005 | Alat Laminasi | Kuas 5" | 145 | 30 | Pcs
Consumable | CN00006 | Alat Laminasi | Kuas 2" | 145 | 230 | Pcs
Consumable | - | ATK | Laptop & Mouse | 145 | 4 | Pcs
Consumable | - | ATK | Printer | 145 | 2 | Pcs
Consumable | - | ATK | Tinta Printer | 145 | 39 | Pcs
Consumable | - | ATK | White Marker | 145 | 120 | Pcs
Consumable |  | ATK | Alat Tulis Kantor | 1 | 1 | Lot
Consumable | - | Jasa Printing | Fotocopy | 1 | 1 | Lot
Consumable | CN00007 | Lain-Lain | Kape | 145 | 180 | Pcs
Consumable | CN00111 | Lain-Lain | Gayung | 145 | 180 | Pcs
Consumable | CN00008 | Lain-Lain | Plastic Cup | 145 | 300 | Pcs
Consumable | CN000014 | Lain-Lain | Ember 10 kg | 145 | 130 | Pcs
Consumable | CN000015 | Lain-Lain | Ember 5 Kg | 145 | 130 | Pcs
Consumable | CN00017 | Lain-Lain | Kain Majun | 145 | 260 | Kg
Consumable | CN00013 | Lain-Lain | Drill Bit | 145 | 30 | Pcs
Consumable | - | Lain-Lain | Sarung Tangan Karet | 145 | 38 | Losin
Consumable | - | Lain-Lain | Sarung Tangan Kain | 145 | 90 | Losin
Consumable | - | Lain-Lain | Dokumen & Laporan | 1 | 1 | Lot
Consumable | - | Material | LPG | 145 | 50 | Kg
Consumable | - | Material | Primer weld-on P70 (1 Pinyt kaleng kecil) | 145 | 36 | Pint
Consumable | - | Material | Adhesive Weld-On P717 PVC | 145 | 72 | Pint
Consumable | - | Material | Welding Rod PVC | 145 | 20 | kg
Consumable | CN000016 | Material | Aceton | 145 | 270 | Liter
Consumable | CN01973 | Material | Gelas Ukur | 145 | 2 | Pcs
Consumable | CN01989 | Material | Thinner | 145 | 260 | Kg
Consumable | CN01974 | Material | Plastik cor | 145 | 40 | Roll
Consumable | CN00019 | Material | Oxygent | 145 | 50 | Tabung
Consumable | CN00020 | Material | Acetylene | 145 | 50 | Tabung
Consumable | - | Material | Electroda RB 32 Bohler / Sejenis | 145 | 504 | Pint
Consumable | - | Material | Kawat Putih Scafolding Asiba | 145 | 20 | Roll
Tools Equipment
Tools Equipment | - | Alat Kerja | Monkey Wrench | 145 | 3 | Unit
Tools Equipment | - | Alat Kerja | Manifold | 145 | 2 | Unit
Tools Equipment | VT00012 | Alat Kerja | Bor Machine | 145 |  | Unit
Tools Equipment | VT00005 | Alat Kerja | Hand Mixer | 145
Tools Equipment | VT00006 | Alat Kerja | Hand Gerinda 4" | 145 | 38 | Unit
Tools Equipment | Vt00006 | Alat Kerja | Hand Gerinda 6" | 145 | 39 | Unit
Tools Equipment | - | Alat Kerja | Hand Torque Machine Lion. 25 | 145 | 1 | Unit
Tools Equipment | - | Alat Kerja | Thermos Oven Elektrode Las 25-50 Kg | 145 | 3 | Unit
Tools Equipment | - | Alat Kerja | Ing Dryer | 145 | 3 | Unit
Tools Equipment | - | Alat Kerja | Mesin Gerinda Potong 14" | 145 | 3 | Unit
Tools Equipment | - | Lainnya | Nozzle Torch Las | 145 | 3 | Unit
Tools Equipment | - | Asset Machine | Bevelling Machine | 145 | 2 | Unit
Tools Equipment | - | Lainnya | Kunci Torsi / Torque Wrench | 145 | 2 | Unit
Tools Equipment | VT00008 | Alat Kerja | Hole Saw | 145 | 2 | Pcs
Tools Equipment | VT00037 | Alat Kerja | Jig Saw | 145 | 1 | Pcs
Tools Equipment | VT00010 | Alat Kerja | Kunci Pas | 145 | 6 | Set
Tools Equipment | VT00011 | Alat Kerja | Mesin Las Portable | 145 | 8 | Unit
Tools Equipment | VT00012 | Alat Kerja | Drill Machine/Mesin Bor | 145 | 3 | Pcs
Tools Equipment | - | Alat Kerja | Mesin Las PVC - CPVC Wipro | 145 | 6 | Unit
Tools Equipment | - | Alat Kerja | Water Pass | 145 | 10 | Unit
Tools Equipment | - | Asset Machine | Pressure Gauge | 145 | 2 | Unit
Tools Equipment | - | Asset Machine | Pompa Hydrotest | 145 | 1 | Unit
Tools Equipment | - | Electricity | Kabel Panel box roll 50 M | 145 | 4 | Roll
Tools Equipment | VT00019 | Electricity | Colokan / Legrant | 145 | 52 | Pasa
Tools Equipment | VT00020 | Electricity | Stop Kontak | 145 | 17 | Pcs
Tools Equipment | VT00015 | Electricity | Kabel listrik 20 M (Roll) | 145 | 5 | Roll
Tools Equipment | VT00024 | Electricity | Panel Box | 145 | 5 | Unit
Tools Equipment | VT00023 | Electricity | BBM Genset | 145 | 504 | Liter
Tools Equipment | VT00035 | Lainnya | Shackle 1-3/8" | 145 | 6 | Pcs
Tools Equipment | VT00025 | Lainnya | Kunci Drum Resin | 145 | 1 | Pcs
Tools Equipment | VT00029 | Lainnya | Scope / Cangkul | 145 | 2 | Pcs
Tools Equipment | VT00032 | Lainnya | Lampu Tembak | 145 | 10 | Pcs
Tools Equipment | VT00038 | Lainnya | Gergaji Kayu | 145 | 4 | Pcs
Tools Equipment | VT00039 | Lainnya | Obeng +/- | 145 | 8 | Pcs
Tools Equipment | VT00060 | Lainnya | Kunci Scafolding | 145 | 5 | Pcs
Tools Equipment | VT00026 | Lainnya | Pompa Thinner/Aceton | 145 | 1 | Pcs
Tools Equipment | VT00027 | Lainnya | Dudukan Drum Resin | 145 | 1 | Pcs
Tools Equipment | VT00028 | Lainnya | Blower | 145 | 3 | Pcs
Tools Equipment | VT00031 | Lainnya | Vacum water Pump | 145 | 1 | Pcs
Tools Equipment | VT00036 | Lainnya | Palu karet | 145 | 4 | Pcs
Tools Equipment | VT00040 | Lainnya | Cutter | 145 | 100 | set
Tools Equipment | VT00041 | Lainnya | Terpal | 145 | 200 | Mtr
Tools Equipment | VT00042 | Lainnya | Lot/Benang | 145 | 20 | Pcs
Tools Equipment | - | Lifting | Kunci Racet Scaffolding | 145 | 6 | pCS
Tools Equipment | - | Lifting | Chainblock 1.5 Ton | 145 | 13 | Pcs
Tools Equipment | - | Lifting | Chainblock 3 Ton | 145 | 15 | Pcs
Tools Equipment | VT00013 | Lifting | Chainblock 5 Ton | 145 | 2 | Pcs
Tools Equipment | - | Lifting | Wiresling 19mm (3/4") | 145 | 12 | Pcs
Tools Equipment | - | Lifting | Web Sling 3 Ton | 145 | 8 | Pcs
Tools Equipment | - | Lifting | Web Sling 15 Ton | 145 | 1 | Pcs
Tools Equipment | VT00014 | Lifting | Cotrex / Level Block 1,5 Ton | 145 | 5 | Pcs
Tools Equipment | VT00014 | Lifting | Cotrex / Level Block 3 Ton | 145 | 5 | Pcs
Tools Equipment | VT00015 | Lifting | Tali Tambang | 145 | 300 | Mtr
Tools Equipment | VT00016 | Lifting | Sling belt | 145 | 5 | Pcs
Tools Equipment | - | Safety | Helmet | 145 | 80 | Unit
Tools Equipment | - | Safety | Seragam | 145 | 80 | Unit
Tools Equipment | - | Safety | Kacamata Safety | 145 | 80 | Unit
Tools Equipment | - | Safety | Faceshield Helm | 145 | 160 | Unit
Tools Equipment | - | Safety | Sepatu Safety | 145 | 80 | Unit
Tools Equipment | - | Safety | Respirator Drager | 145 | 0 | Unit
Tools Equipment | - | Safety | Cartridge Drager | 145 | 0 | Unit
Tools Equipment | - | Safety | ID Card | 145 | 105 | Unit
Tools Equipment | - | Safety | Sarung Tangan Kulit / Welder / Scaff | 145 | 54 | Losin
Tools Equipment | - | Safety | Refil Kaca Las Hitam | 145 | 120 | Pcs
Tools Equipment | - | Safety | Coverall Suit | 145 | 10 | Unit
Tools Equipment | - | Safety | Masker Kain | 145 | 240 | Pcs
Tools Equipment | - | Safety | Ear Plug | 145 | 120 | Pcs
Tools Equipment | - | Safety | APAR | 145 | 5 | Unit
Tools Equipment | - | Safety | Set Kotak P3K | 145 | 5 | Unit
Tools Equipment | - | Safety | Safety tools | 145 | 1 | Lot
Tools Equipment | VT00001 | Survey & Drawing | Jangka | 145 | 2 | Pcs
Tools Equipment | VT00002 | Survey & Drawing | Busur Drajad | 145 | 2 | Pcs
Tools Equipment | VT00003 | Survey & Drawing | Mistar | 145 | 4 | Pcs
Tools Equipment | VT00004 | Survey & Drawing | Meteran | 145 | 6 | Pcs
Tools Equipment | - | Testing Commisioning | Test Commissioning | 1 | 1 | Lot

## Sheet1 (2) (hidden)
Category | Code | Category Item | Spec : | Qty | Durasi
Manpower
Manpower | MP00028 | Manager | Project Manager | 1
Manpower | MP00025 | Manager | Site Manager | 1
Manpower | MP00037 | Staff | Site Engineer | 2
Manpower |  |  | Supervisor | 3
Manpower | MP00033 | Supervisor | Quality Control | 2
Manpower | MP00032 | Supervisor | HSE | 1
Manpower | MP00049 | Supervisor | Logistic | 2
Manpower | MP00068 | Staff | Surveyor | 1
Manpower | MP00041 | Staff | Drafter | 1
Manpower | MP00048 | Supervisor | Rigger Lifting | 1
Manpower | MP00053 | Staff | Admin & GA | 2
Manpower | MP00058 | Worker Driver | Driver | 1
Manpower | MP00054 | Worker Security | Security | 3
Consumable
Consumable | CN00001 | Alat Laminasi | Roll Kapas 4" | 230
Consumable | CN00002 | Alat Laminasi | Roll Kapas 8" | 115
Consumable | CN00003 | Alat Laminasi | Roll Besi | 30
Consumable | CN00005 | Alat Laminasi | Kuas 5" | 30
Consumable | CN00006 | Alat Laminasi | Kuas 2" | 230
Consumable | CN00007 | Lain-Lain | Kape | 180
Consumable | CN00111 | Lain-Lain | Gayung | 180
Consumable | CN00008 | Lain-Lain | Plastic Cup | 300
Consumable | CN00009 | Abrasive | Sand Paper Disc
Consumable | CN000010 | Abrasive | Diamonds Wheels 4" | 60
Consumable | CN000012 | ATK | White Marker
Consumable | CN000014 | Lain-Lain | Ember 10 kg | 130
Consumable | CN000015 | Lain-Lain | Ember 5 Kg | 130
Consumable | CN000016 | Material | Aceton | 270
Consumable | CN01973 | Material | Gelas Ukur | 2
Consumable | CN00017 | Lain-Lain | Kain Majun | 260
Consumable | CN01989 | Material | Thinner | 260
Consumable | CN01972 | Abrasive | Batu gerinda 4" x 6 " mmt | 450
Consumable | CN01974 | Material | Plastik cor | 40
Consumable | CN02010 | Lain-Lain | Sarung tangan scafolder
Tools | VT00015 | Lifting | Tali tambang | 50 |  | Lifting
Consumable | VT00016 | Lifting | Sling belt | 5
Consumable | VT00018 | Electricity | Kabel Panel box roll 50m | 3
Consumable | VT00019 | Electricity | Colokan / Legrand | 4
Consumable | VT00020 | Electricity | Stop Kontak | 4
Consumable | VT00024 | Electricity | Panel Box | 2
Consumable | VT00025 | Lainnya | Kunci Drum Resin | 2
Consumable | VT00029 | Lainnya | Scope / Cangkul
Consumable | VT00032 | Lainnya | Lampu Tembak | 6
Consumable | VT00038 | Lainnya | Gergaji Kayu | 1
Consumable | VT00039 | Lainnya | Obeng +/- | 4
Consumable | CN00009 | Abrasive | Sand Paper Disc 4" (Amplas Gerinda) | 450
Consumable | CN00019 | Material | Oxygent | 50
Consumable | CN00020 | Material | Acetylene | 50
Consumable |  |  | LPG | 50
Consumable |  |  | Electroda RB 32 Bohler / Sejenis | 504
Consumable |  |  | Primer weld-on P70 (1 Pinyt kaleng kecil) | 36
Consumable |  |  | Adhesive Weld-On P717 PVC | 72
Consumable |  |  | Adhesive Weld-On P724 PVC
Consumable |  |  | Welding Rod PVC | 20
Consumable |  |  | Welding Rod CPVC
Consumable |  |  | Kawat Putih Scafolding Asiba | 20
Consumable |  |  | White Marker | 120
Consumable | CN00013 | Lain-Lain | Drill Bit | 30
Tools
| VT00012 | Alat Kerja | Bor Machine | 2
| VT00001 | Survey & Drawing | Jangka | 2
| VT00002 | Survey & Drawing | Busur Drajad | 4
| VT00003 | Survey & Drawing | Mistar | 6
| VT00004 | Survey & Drawing | Meteran
Theodolite
Bak Ukur
| VT00005 | Alat Kerja | Hand Mixer | 38
| VT00006 | Alat Kerja | Hand Gerinda 4" | 19
| Vt00006 | Alat Kerja | Hand Gerinda 6" | 1
|  |  | Hand Torque Machine Lion. 25 | 3
|  |  | Thermos Oven Elektrode Las 25-50 Kg | 3
|  |  | Ing Dryer | 2
|  |  | Mesin Gerinda Potong 14" | 3
|  |  | Nozzle Torch Las | 2
|  |  | Bevelling Machine | 2
|  |  | Kunci Torsi / Torque Wrench | 10
|  |  | Water Pass | 2
| VT00008 | Alat Kerja | Hole Saw | 1
| VT00037 | Alat Kerja | Jig Saw | 3
|  |  | Monkey Wrench | 6
|  |  | Kunci Racet Scaffolding | 6
| VT00010 | Alat Kerja | Kunci Pas | 6
| VT00011 | Alat Kerja | Mesin Las Portable | 8
| VT00012 | Alat Kerja | Drill Machine/Mesin Bor | 3
|  |  | Mesin Las PVC - CPVC Wipro | 6
|  |  | Chainblock 1.5 Ton | 13
|  |  | Chainblock 3 Ton | 15
| VT00013 | Alat Kerja | Chainblock 5 Ton | 2
|  |  | Wiresling 19mm (3/4") | 12
|  |  | Web Sling 3 Ton | 8
|  |  | Web Sling 15 Ton | 1
| VT00014 | Lifting | Cotrex / Level Block 1,5 Ton | 5
| VT00014 | Lifting | Cotrex / Level Block 3 Ton | 5
| VT00015 | Lifting | Tali Tambang | 300
| VT00035 | Lainnya | Shackle 1-3/8" | 6
Genset 350 kVa
|  |  | Kabel Panel box roll 5 M | 4
| VT00019 | Electricity | Colokan / Legrant | 52
| VT00020 | Electricity | Stop Kontak | 17
| VT00021 | Electricity | Kabel listrik 20 M (Roll) | 5
| VT00022 | Electricity | Alat Check Konduktif
| VT00023 | Electricity | BBM Genset | 504
| VT00024 | Electricity | Panel Box | 5
|  |  | Manifold | 2
|  |  | Pressure Gauge | 2
|  |  | Pompa Hydrotest | 1
| VT00060 | Lainnya | Kunci Scafolding | 5
| VT00025 | Lainnya | Kunci Drum Resin | 1
| VT00026 | Lainnya | Pompa Thinner/Aceton | 1
| VT00027 | Lainnya | Dudukan Drum Resin | 1
| VT00028 | Lainnya | Blower | 3
| VT00029 | Lainnya | Scop/Cangkul | 2
| VT00030 | Lainnya | Portable Heater
| VT00031 | Lainnya | Vacum water Pump | 1
| VT00032 | Lainnya | Lampu Tembak | 10
| VT00033 | Lainnya | Blender
| VT00034 | Lainnya | PI-Tape
| VT00036 | Lainnya | Palu karet | 4
| VT00037 | Lainnya | Jig Saw | 8
| VT00038 | Lainnya | Gergaji Kayu | 4
| VT00039 | Lainnya | Obeng + / - | 8
| VT00040 | Lainnya | Cutter | 100
| VT00041 | Lainnya | Terpal | 200
| VT00042 | Lainnya | Lot/Benang | 20
|  |  | Laptop & Mouse | 4
|  |  | Printer | 2
|  |  | Tinta Printer | 39
Equipment
|  |  | Crane 25 Ton (Include Mob Demob) | 4
|  |  | Mob Demob Crane 25 Ton | 1
Crawler Crane 35 Ton (Include Mob Demob)
Mob Demob Crane 35 Ton
Plat 20 x 5 x 12 mm (Untuk Crane)
Forklift 5 Ton
|  |  | Foco Truck 8 ton | 4
|  |  | Mob Demob Foco | 1
Trolli 2 Ton
Handlift 2 Ton
House
| AK00005 |  | Listrik | 5 |  | Include
| AK00013 | Accomodation & Transportation on Sitw | Biaya Pembuatan Site Office | 1
| AK00020 | Accomodation & Transportation on Sitw | Pulsa | 1
| AK00005 | Accomodation & Transportation on Sitw | Air PDAM | 5
| AK00049 | Accomodation & Transportation on Sitw | Kelengkapan Mess | 1
| AK00005 | Accomodation & Transportation on Sitw | Air Minum | 1
| AK00005 | Accomodation & Transportation on Sitw | Mess Karyawan + Laundry | 1
| AK00020 | Accomodation & Transportation on Sitw | Internet Speedy | 2
|  |  | Management Fee | 1
Administrasi
|  |  | Foto Copy | 1
|  |  | Dokumen & Laporan | 1
|  |  | Alat Tulis Kantor | 1
|  |  | Provisi Bank | 1
APD Pekerja
|  |  | Body Hardness | 80
|  |  | Helmet | 80
|  |  | Seragam | 80
|  |  | Kacamata Safety | 80
|  |  | Faceshield Helm | 160
|  |  | Sepatu Safety | 80
|  |  | Respirator Drager | 0
|  |  | Cartridge Drager | 0
|  |  | ID Card | 105
|  |  | Sarung Tangan Karet | 0
|  |  | Sarung Tangan Kain | 0
|  |  | Sarung Tangan Kulit / Welder / Scaff | 0
|  |  | Refil Kaca Las Hitam | 120
|  |  | Coverall Suit | 10
|  |  | Masker Kain | 240
|  |  | Ear Plug | 120
|  |  | APAR | 5
|  |  | Set Kotak P3K | 5
|  |  | Safety tools | 1
Rental Head Office
|  |  | Scafolding Main Frame MF - 190 | 800
|  |  | Cross Brace 220 | 800
|  |  | Base Jack S 60 | 1600
|  |  | U Head jack S 60 | 1600
|  |  | Join Pin | 1600
Asiba Uk. 30 cm x 200 cm
Transport
| AK00046 | Mob Demob Equipment | Mobdemob Material | 1
| AK00024 | Accomodation & Transportation On site | Bus 50 Seat | 1 | 5
| AK00025 | Accomodation & Transportation On site | Truck 125 PS | 1 | 5
| AK00026 | Accomodation & Transportation On site | Pick Up | 1 | 5
| AK00014 | Accomodation & Transportation On site | Mini bus (Avanza Staff Akomodasi) | 1 | 5
Selling
|  |  | BBM | 2000 | 1
Mob Demob Pekerja
|  | Tiket | Tiket Pesawat PP | 60 | 1
|  | Transportasi | Transportasi Darat ke Project | 60 | 1
| AK00034 | Biaya Lain-Lain | Biaya Keamanan Project | 1 | 1
| AK00017 | Biaya Lain-Lain | MCU Team dan Pekerja | 80 | 1
| AK00003 | Biaya Lain-Lain | Biasa LSM | 1 | 1
| AK00035 | Biaya Lain-Lain | Biaya Sertifikasi | 1 | 1
| AK00037 | Biaya Lain-Lain | Biaya Tak Terduga | 1 | 1
|  |  | Test Commisioning | 1 | 1
| AK00039 | Accomodation & Transportation on Site | Biaya Pengobatan | 1 | 2
| AK00001 | Biaya Lain-Lain | Biaya Entertain | 1 | 1